## Slide 1
Addressing Student Capacity
Operational Briefing
October 2018

## Slide 2
Balancing Enrollment and Capacity

## Slide 3
Annual Growth Trends
Does not include Pre-K
491 Increase
w/ Pre-K
Notes: Will update with correct 20th and 40th day numbers for this year when we receive them from Richard

## Slide 4
Notes: Will need to update when 40th day info comes in.

## Slide 5
Capacity Analysis
Elementary BEP Capacity
BEP Capacity with portables
Enrollment
Growth trends
95% Utilization
Middle School BEP Capacity
BEP Capacity with portables
Enrollment
Growth trends
102% Utilization
High School BEP Capacity
Enrollment
Growth trends
91% Utilization
8 Schools > 100%
4 Schools > 100%
1 Schools > 100%
Notes: Elementary yearly growth trend of 12 classrooms
Middle yearly growth trend of 18.5 classrooms
High yearly growth trend of 11 classrooms

## Slide 6
West Creek
Northeast
New Prov./NWHS
M. Central
Richview/CHS
Kenwood
Rossview
M 88%
H 73%
M 103%/
H 78%
M 94%/92%
H 80%
M 115%/94%
H 99%
M 95%
H 92%
M 110%/95%
H 106%/104%
M 110%/99%
H 85%
2018-2019 Middle/High School Capacities
20
Capacity Status – Enrollment
Greater than 100%
90% - 100%
70% - 90%
Less than 70%
3
1
5
4
2
Notes: Once the addition are completed and in use
NEMS will be 97%/86%
NEHS will be 85%

## Slide 7
West Creek
Northeast
New Prov./NWHS
M. Central
Richview/CHS
Kenwood
Rossview
M 88%
H 73%
M 103%/
H 78%
M 94%/92%
H 80%
M 98%/82%
H 85%
M 95%
H 92%
M 110%/95%
H 106%/104%
M 110%/99%
H 85%
2018-2019 Middle/High School Capacities After Additions
20
Capacity Status – Enrollment
Greater than 100%
90% - 100%
70% - 90%
Less than 70%
3
1
5
4
2
Notes: Once the addition are completed and in use
NEMS will be 97%/86%
NEHS will be 85%

## Slide 8
2018-2019 Elementary School Capacities
116%/ 92%
20
Capacity Status – Enrollment
Greater than 100%
90% - 100%
70% - 90%
Less than 70%
89%
78%
101%/98%
79%
95%/81%
98% / 91%
83%
104%/94%
85%
96%/89%
94%/90%
90%
102%/93%
76%/84%
91%/87%
93%
85%
Rossview
Oakland
Carmel
Northeast
81%
114%/96%
103%/95%
103%/91%
Woodlawn
Montgomery Central
Cumberland Heights
Barkers Mill
Sango
Pisgah
Hazelwood
Barksdale
East Montgomery
Ringgold
Byrns Darden
Minglewood
Liberty
West Creek
St Bethlehem K-2
Burt 3-5
Norman Smith
Glenellen
Moore
Kenwood
3
1
5
4
2
112%/96%
Notes: Once the addition are completed
Barkers Mill will be 94%/81%
Minglewood will be 83%/78%

## Slide 9
2018-2019 Elementary School Capacities After Additions
86%/ 72%
20
Capacity Status – Enrollment
Greater than 100%
90% - 100%
70% - 90%
Less than 70%
89%
78%
101%/98%
79%
95%/81%
98% / 91%
83%
84%/77%
85%
96%/89%
94%/90%
90%
102%/93%
76%/84%
91%/87%
93%
85%
Rossview
Oakland
Carmel
Northeast
81%
114%/96%
103%/95%
103%/91%
Woodlawn
Montgomery Central
Cumberland Heights
Barkers Mill
Sango
Pisgah
Hazelwood
Barksdale
East Montgomery
Ringgold
Byrns Darden
Minglewood
Liberty
West Creek
St Bethlehem K-2
Burt 3-5
Norman Smith
Glenellen
Moore
Kenwood
3
1
5
4
2
112%/96%
Notes: Once the addition are completed
Barkers Mill will be 94%/81%
Minglewood will be 83%/78%

## Slide 10
Region 1
Region 2
Region 3
Region 4
Region 5
CMCSS Portable Distribution By Zoning Regions
Portables in District
Total = 83
Square Footage = 85,201
Number of Seats = 1,974
Notes: 80% of all portables are between Zoning Region 1&2

## Slide 11
HS Capacity per GL= 2735 (Current)
MS Capacity per GL= 2690 (Current)
Notes: 472 additional students in current K-2 that will put us 18 classrooms above current middle school capacity
314 additional students in current K-3 that will put us 11 classrooms above current high school capacity

## Slide 12
Facilities Planning and Construction

## Slide 13: 2017-2021 Building Program
Phase 1
Notes: This is the CMCSS Building Program
Budget Committee and CMCSS came up with approved by a resolution by County Commissioners
4 Projects were bid on Jan 2018 for $14,570,746 million dollars

## Slide 14
Notes: Started in March proceeding on schedule as of September.
Approximately 60 % complete and on benchmark as of today.
They are approaching 80% complete with minor impacts do to weather

## Slide 15: Timeline Design & Construction
Notes: In the last stages of Construction
making preparation for turn over in Nov + Dec timeframe with being operational in Jan 2019

## Slide 16
Minglewood Elementary
Description:
16,194 Square foot addition with 12 classrooms, two restrooms, mechanical, technology, and transportation site modifications
BEP: 792  990
Financial Summary: | BID
Building Construction | $2,917,594
Equipment/Tech./Furniture/Oth | $200,000
 | $3,117,594

## Slide 17
Barkers Mill Elementary
Description:
14,886 Square foot addition with 12 Classrooms, Two Restrooms, mechanical, technology, connector, and minor site modifications
BEP: 842  1,140
Financial Summary: | BID
Building Construction | $2,604,073
Equipment/Tech./Furniture/Oth | $200,000
 | $2,804,073

## Slide 18
Northeast Middle School
Description:
17,152 Square foot addition with 10 classrooms, two restrooms, mechanical, technology, connector, and transportation site modifications
BEP: 1,096  1,285
Financial Summary: | BID
Building Construction | $2,810,317
Equipment/Tech./Furniture/Oth | $200,000
 | $3,010,317

## Slide 19
Northeast High School
Description:
24,750 Square foot addition with 12 classrooms, auxiliary gymnasium, two restrooms, offices, mechanical, technology, ADA delivery area, kitchen serving line renovation, and minor site modifications
BEP: 1,470  1,705
Financial Summary: | BID
Building Construction | $5,438,762
Equipment/Tech./Furniture/Oth | $200,000
 | $5,638,762

## Slide 20
Facilities Planning and Construction Next Steps

## Slide 21: 2017-2021 Building Program
3 Projects
January 2019
$50.3 Million Total
Phase 2

## Slide 22
Building New Capacity
Staff Recommendation
Seek design approval for two elementary additions and one new middle school to begin in January 2019
Phase One Projects are nearing completion
Continued overcrowding in zoning regions I & II
More students in middle schools than available capacity.

## Slide 23
Questions?